## Sheet1
user Management by Admin & User Operation |  | Item | Strat Date | End date | Resource | Status
| Server | user creation from admin for both the ccare and the GH | 2016-08-08 | 2016-08-08 | Rajendra | completed
| Server | user login with token authentication | 2016-09-08 | 2016-09-08 | Rajendra | completed
| Server | account setting crud operation | 2016-10-08 | 2016-10-08 | Rajendra | completed
| Server | forget password - email verification | 15/8/16 | 15/8/16 | Rajendra | Yet to Start
| Server | change password | 16/8/16 | 16/8/16 | Rajendra | Yet to Start
| Server | logout | 2016-11-08 | 2016-11-08 | Rajendra | completed
| client | user creation from admin for both the ccare and the GH | 16/08/2016 | 17/08/2016 | Rajashree | Yet to Start
| client | user login with token authentication | 2016-09-08 | 2016-09-08 | Rajendra | completed
| client | account setting crud operation | 16/08/2016 | 17/08/2016 | Santosh | Yet to Start
| client | forget password - email verification | 19/08/2016 | 19/08/2016 | Rajashree | Yet to Start
| client | change password | 20/08/2016 | 20/08/2016 | Rajashree | Yet to Start
| client | logout | 2016-11-08 | 2016-11-08 | Rajendra | completed
| client | Modular Auhentication | 17/08/2016 | 18/08/2016 | Rajendra | Yet to Start